## Sheet1
Property Management
2021-05-29
Project Name: V Write For You |  | Property Management
ID No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
1221 | 1 | Executive Support | There are increased chances of risk. The most serious danger is a lack of executive support. The project should have specific responsibilities from the top level administration. | Structure/Process risk | Commitment from executives | Dissatisfaction of executives | Risk Avoidance | Project Manager | Medium-Low | High | Avoided
1222 | 2 | Cash flow | There are increased chances of risk. Extending the project's budget limit may result in increased software costs and asset payments, among other things, due to a variety of variables. | Financial Risk | Increase in price of softwares and resource wages | Salary Increments | Risk Acceptance | Finance Manager | High | High | Anticipated
1223 | 3 | Scope | There are increased chances of risk. There is a huge risk if the quality, dependencies, and scope management estimations are incorrect, or if the theory is incorrect. | Structure/Process risk | Wrong estimation | Client Dissatisfaction | Risk avoidance | Project Manager | Low | High | Avoided
1224 | 4 | Stakeholders | Risk chances are medium. In the event that partners has negative demeanor towards an project or no collaboration between them, at that point it is a barricade to the task. | Process Risk | Lack of cooperation between stakeholders | Meeting Reviews | Risk avoidance | Program Manager | Low | Medium | Mitigated
1225 | 5 | Resources and Team | Risk chances are medium. In the event that the assets are leaving organization or unpracticed colleagues with legitimate range of abilities. | People Risk | Lack of resources with proper skill set | Dissatisfaction of Employees | Risk Mitigation | Project Manager | Low | Medium | Anctipated
1226 | 6 | Existence of similar software in the market | Risk chances are medium. On the off chance that there is a comparable consulting firm that creates sites, it can lessen the ubiquity of the organization. | Market Risk | Availability of similar products in the market | Application | Risk Acceptance | Program Manager | Medium-High | Medium | Anctipated
1227 | 7 | Recession in market | Risk chances are medium. Changes in market demands that cause shares to increment and diminishing with no particular specific pattern. | Market Risk | Recession | Lacking of proactiveness on analying market | Risk Acceptance | Organization | Low Risk | Medium | Anctipated
1228 | 8 | Natural Disasters | Risk chances are high. The weather is out of control. We'll need to make measures to keep a strategic space between us and them. | Financial Risk | Being not ready to face the risk | No before proper preparations | Risk Acceptance | Organization | Medium-High | High | Anctipated
1229 | 9 | Late completion of testing | Risk chances are high. Guarantee legitimate observing set up and utilized adequately. | Process Risk | Time constraints would not be same | Lacking of time in schedules | Risk Acceptance | Project Manager | High | High | Mitigated
1230 | 10 | Defective Server | The likelihood of danger is high. Place reinforcement servers in place, and evaluate a warm-site business recovery plan. | Process Risk | Main server crash would cause business losses | No proper backups | Risk Acceptance | Project Manager | High | High | Anticipated