## Sheet1
Issue Log
Date:06/01/2021
Issue No. | Description | Impact | Date Reported | Reported By | Assigned To | Priority (H/M/L) | Due date | Status | Comments
1 | The team members' concerns about business are preventing the project from progressing beyond the preliminary stage. | There will be a significant delay. | 10th May | Aneela | Manisha | M | 19th May | Open | Could address and resolve individual concerns We've also begun team-building exercises.
2 | Internet speed has slowed down. | Communication and job delays | 12th May | Sowmya | Sumithra | M | 20th May | Closed | Network difficulties were resolved, and the system was updated to high-speed wireless internet.
3 | Training times are longer than intended. | Delay in schedule | 14th May | Padmini | Manisha | M | 21th May | Closed | Team members faced difficulties in learning new software
4 | Scope creep | Re-do your finances and planning. | 17th May | Manisha | Sowmya | M | 23th May | Closed | Since the sponsor discovered potential add-ons, the team had to repeat the procedure, which took more time and money.
5 | Team member's absence | Slower pace of work | 24th May | Sowmya | Sumithra | M | 25th May | Closed | Since the project manager was ill, the work speed was slowed.
6 | Increment in cost of resources | Due to a scarcity of resources, work progress has been slowed. | 30th May | Sumithra | Aneela | H | 2020-05-26 | Open | Due to the state's lockdown, there was a scarcity of supplies and a high demand, raising the price.
7 | Server problem | Delay in the schedule/plan | 1st June | Aneela | Padmini | H | 4th June | Open | Applied good query optimization techniques and SQL tuning
8 | Accessibility Issues for Users | Delay in the plan | 2nd June | Padmini | Sumithra | M | 3rd June | Open | User acces was denied,So the work pace was reduced.